## Effort Estimation
Phase | Version | Deliverables | Task | Assignee | Effort Estimation | Actual | Status
Design | V3.0.0 | Use Case Diagram | Identify Actors | Mohamed Sameh | 3 H/Week | 1 | Completed | Open/To Do | On Hold
|  |  | Define Use Cases |  | 3 H/Week | 2 | Completed | Completed | Pending Review
|  |  | Map Interactions |  | 3 H/Week | 2 | Completed | Cancelled | In Progress
|  |  | Refine and Validate |  | 5 H/Week | 4 | Completed
|  |  | System Boundary |  | 3 H/Week | 4 | Completed
|  |  | Relationships |  | 5 H/Week | 4 | Completed
|  | HL Description | Define the Software Scope | Amir Ahmed | 4 H/Week | 1 | Completed
|  |  | Outline Key Features |  | 4 H/Week | 2024-01-05 | Completed
|  |  | Describe User Interactions |  | 5 H/Week | 4 | Completed
|  |  | Highlight Data Flow |  | 3 H/Week | 4 | Completed
|  | ERD | Identify the Entities | Eslam Reda | 4 H/Week | 1 | Completed
|  |  | Define the Relationships |  | 4 H/Week | 4 | Completed
|  |  | Add Attributes |  | 4 H/Week | 4 | Completed
|  |  | Refine the Diagram |  | 5 H/Week | 4 | Completed
|  |  | Validate and Review |  | 5 H/Week | 4 | Completed
|  | Wireframe and UI Design | Define the Goal | Merna Hesham | 6 H/Week | 1 | Completed
|  |  | Research and Analysis |  | 6 H/Week | 3 | Completed
|  |  | Design and Build |  | 6 H/Week | 4 | Completed
|  |  | Implement the Framework |  | 5 H/Week | 3 | Completed
|  |  | Monitor and Evaluate |  | 5 H/Week | 4 | Completed
|  | Timeline and Task Assignment | Gather Information | Merna Hesham | 3 H/Week | 2 | Completed
|  |  | Revising task durations |  | 3 H/Week | 2 | Completed
|  |  | Task Assignment Updates |  | 3 H/Week | 2 | Completed
|  |  | Communicate the Changes |  | 3 H/Week | 2 | Completed
|  |  | Monitor and Adapt |  | 3 H/Week | 3 | Completed
|  | Flow Chart | Create Client Login Flowchart | Eslam Reda | 3 H/Week | 3 | Completed
|  |  | Create Client Signup Flowchart | Mohamed Sameh | 3 H/Week | 3 | Completed
|  |  | Create Client View Transactions Flowchart | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Create Supplier Sell Products Flowchart | Amir Ahmed | 3 H/Week | 3 | Completed
|  |  | Create Supplier Edit Products Flowchart | Amir Ahmed | 3 H/Week | 3 | Completed
|  |  | Create Client Buy Products Flowchart | Eslam Reda | 3 H/Week | 3 | Completed
|  |  | Create Admin Delete Client Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  |  | Create Admin Delete Products Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  |  | Create Admin View Clients Transactions Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  |  | Create Admin View Clients Transactions Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Admin View Clients Transactions Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Admin View Clients Transactions Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Admin Sign out Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Client Sign out Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Supplier Sign out Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  | Class Diagram + Interfaces | Identify Classes | Samar Salah | 3 H/Week | 3 | Completed
|  |  | List Attributes and Methods |  | 3 H/Week | 3 | Completed
|  |  | Identify Relationships |  | 3 H/Week | 3 | Completed
|  |  | Create Class Boxes |  | 3 H/Week | 3 | Completed
|  |  | Add Attributes and Methods | Eslam Reda | 3 H/Week | 3 | Completed
|  |  | Draw Relationships |  | 3 H/Week | 3 | Completed
|  |  | Label Relationships |  | 3 H/Week | 3 | Completed
|  |  | Review and Refine |  | 3 H/Week | 3 | Completed
|  | Update | RTM | Merna Hesham | 3 H/Week | 2 | Completed
|  |  | SRS |  | 3 H/Week | 2 | Completed
|  |  | Effort Estimations |  | 3 H/Week | 2 | Completed
|  |  | Github Repository |  | 3 H/Week | 3 | Completed
|  |  | CMP | Samar Salah | 2 H/Week | 1 | Completed
|  | Sequence Diagram | Create Client Login | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Create Client Signup | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Create Admin Signout | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Client Signout | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Supplier Signout | Merna Hesham | 2 H/Week | 1 | Completed
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress
In Progress

## Capacity
Phase | Member Name | Availablity | Planneed Time | Actual Time
Sprint 1 (Project Management) | Mohamed Sameh | 10 | 10 | 8
| Amir Ahmed | 10 | 10 | 8
| Eslam Reda | 10 | 10 | 8
| Merna Hesham | 10 | 10 | 9
| Sohaila Ashraf | 10 | 10 | 8
| Samar Salah | 10 | 10 | 7
Sprint 2 | Mohamed Sameh | 10 | 10 | 7
| Amir Ahmed | 10 | 10 | 7
| Eslam Reda | 10 | 10 | 8
| Merna Hesham | 10 | 10 | 9
| Sohaila Ashraf | 10 | 10 | 8
| Samar Salah | 10 | 10 | 6
Sprint 3 (Design) | Mohamed Sameh | 10 | 10 | 8
| Amir Ahmed | 10 | 10 | 6
| Eslam Reda | 10 | 10 | 8
| Merna Hesham | 10 | 10 | 9
| Sohaila Ashraf | 10 | 10 | 8
| Samar Salah | 10 | 10 | 5
Sprint 4 | Mohamed Sameh
Amir Ahmed
Eslam Reda
Merna Hesham
Sohaila Ashraf
Samar Salah
Sprint 5 | Mohamed Sameh
Amir Ahmed
Eslam Reda
Merna Hesham
Sohaila Ashraf
Samar Salah
Sprint 6 | Mohamed Sameh
Amir Ahmed
Eslam Reda
Merna Hesham
Sohaila Ashraf
Samar Salah