## Effort Estimation
Phase | Version | Deliverables | Task | Assignee | Effort Estimation | Actual | Status
Design | V3.0.0 | Use Case Diagram | Identify Actors | Mohamed Sameh | 3 H/Week | 1 | Completed | In Progress
|  |  | Define Use Cases |  | 3 H/Week | 2 | Completed | Pending Review
|  |  | Map Interactions |  | 3 H/Week | 2 | Completed | On Hold
|  |  | Refine and Validate |  | 5 H/Week | 4 | Completed | Open/To Do
|  |  | System Boundary |  | 3 H/Week | 4 | Completed | Completed
|  |  | Relationships |  | 5 H/Week | 4 | Completed | Cancelled
|  | HL Description | Define the Software Scope | Amir Ahmed | 4 H/Week | 1 | Completed
|  |  | Outline Key Features |  | 4 H/Week | 2024-01-05 | Completed
|  |  | Describe User Interactions |  | 5 H/Week | 4 | Completed
|  |  | Highlight Data Flow |  | 3 H/Week | 4 | Completed
|  | ERD | Identify the Entities | Eslam Reda | 4 H/Week | 1 | Completed
|  |  | Define the Relationships |  | 4 H/Week | 4 | Completed
|  |  | Add Attributes |  | 4 H/Week | 4 | Completed
|  |  | Refine the Diagram |  | 5 H/Week | 4 | Completed
|  |  | Validate and Review |  | 5 H/Week | 4 | Completed
|  | Wireframe and UI Design | Define the Goal | Merna Hesham | 6 H/Week | 1 | Completed
|  |  | Research and Analysis |  | 6 H/Week | 3 | Completed
|  |  | Design and Build |  | 6 H/Week | 4 | Completed
|  |  | Implement the Framework |  | 5 H/Week | 3 | Completed
|  |  | Monitor and Evaluate |  | 5 H/Week | 4 | Completed
|  | Timeline and Task Assignment | Gather Information | Merna Hesham | 3 H/Week | 2 | Completed
|  |  | Revising task durations |  | 3 H/Week | 2 | Completed
|  |  | Task Assignment Updates |  | 3 H/Week | 2 | Completed
|  |  | Communicate the Changes |  | 3 H/Week | 2 | Completed
|  |  | Monitor and Adapt |  | 3 H/Week | 3 | Completed
|  | Flow Chart | Create Client Login Flowchart | Eslam Reda | 3 H/Week | 3 | Completed
|  |  | Create Client Signup Flowchart | Mohamed Sameh | 3 H/Week | 3 | Completed
|  |  | Create Client View Transactions Flowchart | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Create Supplier Sell Products Flowchart | Amir Ahmed | 3 H/Week | 3 | Completed
|  |  | Create Supplier Edit Products Flowchart | Amir Ahmed | 3 H/Week | 3 | Completed
|  |  | Create Client Buy Products Flowchart | Eslam Reda | 3 H/Week | 3 | Completed
|  |  | Create Admin Delete Client Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  |  | Create Admin Delete Products Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  |  | Create Admin View Clients Transactions Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  |  | Create Admin Sign out Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Client Sign out Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Supplier Sign out Flowchart | Merna Hesham | 2 H/Week | 1 | Completed
|  | Class Diagram + Interfaces | Identify Classes | Samar Salah | 3 H/Week | 3 | Completed
|  |  | List Attributes and Methods |  | 3 H/Week | 3 | Completed
|  |  | Identify Relationships |  | 3 H/Week | 3 | Completed
|  |  | Create Class Boxes |  | 3 H/Week | 3 | Completed
|  |  | Add Attributes and Methods | Eslam Reda | 3 H/Week | 3 | Completed
|  |  | Draw Relationships |  | 3 H/Week | 3 | Completed
|  |  | Label Relationships |  | 3 H/Week | 3 | Completed
|  |  | Review and Refine |  | 3 H/Week | 3 | Completed
|  | Update | RTM | Merna Hesham | 3 H/Week | 2 | Completed
|  |  | SRS |  | 3 H/Week | 2 | Completed
|  |  | Effort Estimations |  | 3 H/Week | 2 | Completed
|  |  | Github Repository |  | 3 H/Week | 3 | Completed
|  |  | CMP | Samar Salah | 2 H/Week | 1 | Completed
|  | Sequence Diagram | Create Client Login | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Create Client Signup | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Create Admin Signout | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Client Signout | Merna Hesham | 2 H/Week | 1 | Completed
|  |  | Create Supplier Signout | Merna Hesham | 2 H/Week | 1 | Completed
Code | V4.0.0 | Update HL Description | Define the Software Scope | Amir Ahmed | 3 H/Week | 2 | Completed
|  |  | Outline Key Features |  | 3 H/Week | 2 | Completed
|  |  | Describe User Interactions |  | 3 H/Week | 2 | Completed
|  |  | Highlight Data Flow |  | 3 H/Week | 2 | Completed
|  | Update Wireframe and UI Design | Define the Goal | Merna Hesham | 6 H/Week | 1 | Completed
|  |  | Research and Analysis |  | 6 H/Week | 3 | Completed
|  |  | Design and Build |  | 6 H/Week | 4 | Completed
|  |  | Implement the Framework |  | 5 H/Week | 3 | Completed
|  |  | Monitor and Evaluate |  | 5 H/Week | 4 | Completed
|  | Timeline and Task Assignment | Gather Information | Samar Salah |  |  | Open/To Do
|  |  | Revising task durations |  |  |  | Open/To Do
|  |  | Task Assignment Updates |  |  |  | Open/To Do
|  |  | Communicate the Changes |  |  |  | Open/To Do
|  |  | Monitor and Adapt |  |  |  | Open/To Do
|  | Update Flow Chart | Update Login Flowchart | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Update Signup Flowchart | Mohamed Sameh | 3 H/Week | 3 | Completed
|  |  | Update Supplier Sell Products Flowchart | Amir Ahmed | 3 H/Week | 3 | Completed
|  |  | Update Supplier Edit Products Flowchart | Amir Ahmed | 3 H/Week | 3 | Completed
|  |  | Update Client Buy Products Flowchart | Eslam Reda | 3 H/Week | 3 | Completed
|  |  | Update Admin Delete Client Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  |  | Update Admin Delete Products Flowchart | Sohaila Ashraf | 3 H/Week | 3 | Completed
|  | Update Class Diagram + Interfaces | Update Class Supplier | Sohaila Ashraf | 3 H/Week | 1 | Completed
|  |  | Update Class Client | Amir Ahmed | 3 H/Week | 1 | Completed
|  |  | Update Class Admin | Sohaila Ashraf | 3 H/Week | 1 | Completed
|  |  | Update Class Signup | Mohamed Sameh | 3 H/Week | 1 | Completed
|  |  | Update Class Login | Eslam Reda | 3 H/Week | 1 | Completed
|  |  | Update Class Product | Amir Ahmed | 3 H/Week | 1 | Completed
|  | Update | RTM | Amir Ahmed | 3 H/Week | 2 | Completed
|  |  | SRS | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Effort Estimations | Merna Hesham Samar Salah | 3 H/Week | 2 | Completed
|  |  | Github Repository | Merna Hesham | 3 H/Week | 3 | Completed
|  | Sequence Diagram | Update Login | Merna Hesham | 3 H/Week | 3 | Completed
|  |  | Update Signup | Merna Hesham | 2 H/Week | 1 | Completed
|  | Creation and Update | High level Design Document | Merna Hesham | 3 H/Week | 2 | Completed
|  |  | Low level Design Document | Merna Hesham | 3 H/Week | 2 | Completed
|  | Implement Frontend Design | about.html | Samar Salah | 5 H/Week | 5 | Completed
|  |  | admin_accessories.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | admin_clothes.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | admin_main.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | admin_remove_clients.html | Mohamed Sameh | 5 H/Week | 5 | Completed
|  |  | admin_view_clients_transactions.html | Mohamed Sameh | 5 H/Week | 5 | Completed
|  |  | Base Login.html | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | Base Sign Up.html | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | base.html | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | client_accessories.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | client_account_cart.html | Mohamed Sameh | 5 H/Week | 5 | Completed
|  |  | client_add_to_cart.html | Eslam Reda | 5 H/Week | 5 | Completed
|  |  | client_buy_products.html | Eslam Reda | 5 H/Week | 5 | Completed
|  |  | client_clothes.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | client_main.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | client_view_transactions.html | Eslam Reda | 5 H/Week | 5 | Completed
|  |  | contact.html | Samar Salah | 5 H/Week | 5 | Completed
|  |  | empty_transaction.html | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | login.html | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | signup.html | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | supplier_accessories.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | supplier_clothes.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | supplier_edit_product.html | Eslam Reda | 5 H/Week | 5 | Completed
|  |  | supplier_main.html | Amir Ahmed | 5 H/Week | 5 | Completed
|  |  | supplier_sell_product.html | Eslam Reda | 5 H/Week | 5 | Completed
|  |  | admin_accessories | Amir Ahmed | 5 H/Week | 5 | Completed
|  | Backend Design | Create Structure of the website | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | Create app.py | Merna Hesham | 15 H/Week | 16 | Completed
|  |  | Create createDB.py | Merna Hesham | 6 H/Week | 5 | Completed
|  |  | Create db.py | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | Create style.css | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | Create script.js | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | Images | Merna Hesham | 5 H/Week | 5 | Completed
|  |  | Create queries for DB | Sohaila Ashraf | 5 H/Week | 4 | Completed
|  |  | Create my_db.sqlite | Sohaila Ashraf | 5 H/Week | 4 | Completed

## Capacity
Phase | Member Name | Availablity | Planneed Time | Actual Time
Sprint 1 (Project Management) | Mohamed Sameh | 10 | 10 | 8
| Amir Ahmed | 10 | 10 | 8
| Eslam Reda | 10 | 10 | 8
| Merna Hesham | 10 | 10 | 9
| Sohaila Ashraf | 10 | 10 | 8
| Samar Salah | 10 | 10 | 7
Sprint 2 | Mohamed Sameh | 10 | 10 | 7
| Amir Ahmed | 10 | 10 | 7
| Eslam Reda | 10 | 10 | 8
| Merna Hesham | 10 | 10 | 9
| Sohaila Ashraf | 10 | 10 | 8
| Samar Salah | 10 | 10 | 6
Sprint 3 (Design) | Mohamed Sameh | 10 | 10 | 8
| Amir Ahmed | 10 | 10 | 6
| Eslam Reda | 10 | 10 | 8
| Merna Hesham | 10 | 10 | 9
| Sohaila Ashraf | 10 | 10 | 8
| Samar Salah | 10 | 10 | 5
Sprint 4 (Code) | Mohamed Sameh | 15 | 15 | 12
| Amir Ahmed | 15 | 15 | 12
| Eslam Reda | 15 | 15 | 12
| Merna Hesham | 15 | 15 | 18
| Sohaila Ashraf | 15 | 15 | 15
| Samar Salah | 15 | 15 | 7
Sprint 5 | Mohamed Sameh
Amir Ahmed
Eslam Reda
Merna Hesham
Sohaila Ashraf
Samar Salah
Sprint 6 | Mohamed Sameh
Amir Ahmed
Eslam Reda
Merna Hesham
Sohaila Ashraf
Samar Salah